# CorpusForge — Sprint Plan (4-Week Demo Target)

Author: Jeremy Randall (CoPilot+)

Repo: CorpusForge

Date: 2026-04-04 MDT

Demo Target: 2026-05-02 (aligned with HybridRAG V2)

Dependency: HybridRAG V2 consumes CorpusForge's export packages

## Guiding Principles

**CorpusForge must produce V2-consumable exports by end of Sprint 1.** V2 can't demo without data.

**Reuse V1 code aggressively.** 60-70% of core logic is already written and tested.

**Enrichment and entity extraction are Sprint 2.** Sprint 1 delivers chunks and vectors.

**500 lines per class max** (comments excluded).

**Incremental from day one.** Nightly runs must be fast — minutes, not hours.

## Sprint 1: Core Pipeline (Week 1 — April 5-11)

Goal: Parse, chunk, embed, and export. Produce a package V2 can import and query.

### Slice 1.1: Repo Bootstrap + Config (Day 1)

Initialize git repo, CoPilot+.md, .gitignore, sanitize_before_push.py

Create directory structure

Port Pydantic config schema (source paths, output path, chunk settings, GPU settings)

Write config.yaml

### Slice 1.2: Download & Hash (Day 1-2)

Implement `download/syncer.py` — file copy from configured source directories

Implement `download/hasher.py` — SHA-256 content hashing

Implement `download/deduplicator.py` — _1 suffix detection + content-hash dedup

SQLite file state table (path, hash, mtime, size, status)

### Slice 1.3: Parse (Day 2-3)

Port 32 parsers from V1 — split into individual files under `src/parse/parsers/`

Implement `parse/dispatcher.py` — route by extension

Implement `parse/quality_scorer.py` — score 0.0-1.0

Implement `parse/ocr.py` — pytesseract + Poppler pipeline

Error isolation: try/except per file, never crash pipeline

### Slice 1.4: Chunk + Embed (Day 3-5)

Port `chunk/chunker.py` from V1 (1200/200, sentence boundary)

Port `chunk/chunk_ids.py` — deterministic SHA-256 IDs

Port `embed/embedder.py` — CUDA primary + ONNX fallback

Port `embed/batch_manager.py` — token-budget batching + OOM backoff

Verify: nomic-embed-text v1.5 produces 768-dim float16 vectors

### Slice 1.5: Export + Pipeline Orchestrator (Day 5-7)

Implement `export/packager.py` — write chunks.jsonl + vectors

Implement `export/manifest.py` — generate manifest.json

Implement `pipeline.py` — orchestrate all stages sequentially

Implement `scripts/run_pipeline.py` — CLI entry point

Test: run pipeline on small subset (~100 files), verify V2 can import

### Sprint 1 Exit Criteria

Pipeline runs end-to-end on test corpus

Export package produced with chunks.jsonl + vectors + manifest.json

HybridRAG V2 successfully imports the export package

V2 can answer basic semantic queries against CorpusForge output

Incremental mode works (re-run skips unchanged files)

## Sprint 2: Enrichment + Entity Extraction (Week 2 — April 12-18)

Goal: Add contextual enrichment and first-pass entity extraction to the pipeline.

### Slice 2.1: Contextual Enrichment (Day 1-3)

Implement `enrich/ollama_client.py` — local Ollama API for phi4:14B

Implement `enrich/enricher.py` — generate context prefix per chunk

Enrichment prompt: document title, section heading, topic summary

Incremental: only enrich new/changed chunks (checkpoint tracking)

GPU memory management: phi4:14B (~9GB) + embedder on separate GPU if available

### Slice 2.2: GLiNER2 Entity Extraction (Day 3-5)

Implement `extract/ner_extractor.py` — GLiNER2 zero-shot NER

Entity types: PART_NUMBER, PERSON, SITE, DATE, ORGANIZATION, FAILURE_MODE

Output: candidate_entities.jsonl with confidence scores

Run on CPU (does not compete with GPU for embedding/enrichment)

**Fallback if GLiNER waiver blocked:** skip first-pass, V2 uses GPT-4o for all extraction

### Slice 2.3: Updated Export (Day 5-6)

Add enriched_text to chunks.jsonl

Add entities.jsonl to export package

Update manifest.json with enrichment/extraction stats

Test: V2 imports enriched chunks, BM25 search uses enriched text

### Slice 2.4: Run Report (Day 6-7)

Implement run_report.json generation

Stats: files processed/skipped/failed, chunks created, entities extracted

Timing per stage

Error summary with file paths

### Sprint 2 Exit Criteria

Enriched chunks produce better retrieval in V2 (A/B test on golden queries)

Entity extraction produces candidate entities V2 can validate

Run report provides operational visibility

Full pipeline (download → export) runs end-to-end with all stages

## Sprint 3: GUI + Scheduling (Week 3 — April 19-25)

Goal: Monitoring GUI and automated nightly scheduling.

### Slice 3.1: GUI (Day 1-4)

Implement `gui/app.py` — main Tkinter window (V2 aesthetic)

Implement `gui/progress_panel.py` — pipeline stage, progress bar, ETA

Implement `gui/status_panel.py` — last run stats, error count

Implement `gui/theme.py` — shared dark/light color scheme

"Run Now" button for manual trigger

Run history (last 10 runs)

### Slice 3.2: Scheduling (Day 4-5)

Implement `scripts/schedule_nightly.py` — Windows Task Scheduler setup

Headless mode (no GUI, log to file)

Configurable schedule time in config.yaml

### Slice 3.3: Audit Tool (Day 5-7)

Implement `scripts/audit_index.py` — "what did we process?" report

File counts by format, parse success rate, chunk distribution

Duplicate detection report

Quality score distribution

Entity extraction coverage

### Sprint 3 Exit Criteria

GUI shows real-time pipeline progress

Nightly schedule configured and tested

Audit report provides corpus visibility

## Sprint 4: Production Hardening (Week 4 — April 26 - May 2)

Goal: Run against full production corpus, harden for demo.

### Slice 4.1: Full Corpus Run (Day 1-4)

Run pipeline against full 420K file corpus

Monitor: memory, GPU utilization, disk I/O, timing

Fix any scale-related issues (file handle limits, SQLite locking, etc.)

Verify: V2 import handles full-scale export

### Slice 4.2: Performance Tuning (Day 4-6)

Optimize batch sizes for Beast GPU topology (GPU 0 compute, GPU 1 display)

Optimize SQLite WAL mode for concurrent reads during export

Profile memory usage on full corpus

Target: incremental nightly run < 90 minutes

### Slice 4.3: Demo Prep (Day 6-7)

Verify V2 demo queries work against CorpusForge-produced data

Document: "How to run CorpusForge from scratch"

Document: "How to check if tonight's run succeeded"

Final audit report on production corpus

### Sprint 4 Exit Criteria

Full corpus processed successfully

Incremental nightly run under 90 minutes

V2 demo queries produce correct answers on CorpusForge data

Operator documentation complete

Jeremy Randall | CorpusForge | 2026-04-04 MDT