# Unified Sprint Plan — Walking Skeleton Method

Author: Jeremy Randall (CoPilot+)

Date: 2026-04-04 MDT

Repos: CorpusForge (ingest) + HybridRAG V2 (query)

Demo Target: 2026-05-02 (4 weeks)

Method: Walking Skeleton — thinnest end-to-end path first, then incremental features

Work Mode: Nights and weekends. Agile — every sprint ships something demo-able.

## Guiding Principles

**Skeleton first.** Build the thinnest slice through BOTH apps before adding any features.

**Config first.** Everything reads config. Config is the foundation.

**One feature at a time.** Focused tasks produce better code than monolithic asks.

**Tests alongside.** Golden eval queries from Sprint 1 onward. They're your safety net.

**CorpusForge before V2** for each feature — V2 depends on CorpusForge output.

**Reuse V1 aggressively.** 60-70% of CorpusForge is V1 code. Don't rewrite what works.

**500 lines per class max.** Keeps code reviewable, portable, modular.

**Never build all 8 CorpusForge stages before testing if V2 can import the output.** Prove the handoff works at every stage.

## Sprint 0: Config + Skeleton Wiring (Days 1-3 — April 5-7)

Goal: Both apps boot, config validates, and 1 file flows end-to-end from CorpusForge export to V2 query answer.

### Slice 0.1: Config Schemas (Day 1 — Both Repos)

CorpusForge:

`src/config/schema.py` — Pydantic schema: source paths, output path, chunk size/overlap, embed model, GPU settings

`config/config.yaml` — single config, beast preset defaults

Boot script: load config → validate → print "CorpusForge ready"

HybridRAG V2:

`src/config/schema.py` — Pydantic schema: LanceDB path, SQLite path, LLM settings, retrieval settings, hardware preset

`config/config.yaml` — single config, no modes, beast preset defaults

Boot script: load config → validate → print "V2 ready"

Exit: Both apps boot and validate config without errors.

### Slice 0.2: CorpusForge Minimal Pipeline (Day 1-2)

`src/parse/parsers/txt_parser.py` — parse 1 text file (simplest parser)

`src/chunk/chunker.py` — port from V1 (1200/200, sentence boundary)

`src/chunk/chunk_ids.py` — port from V1 (SHA-256 deterministic IDs)

`src/embed/embedder.py` — port from V1 (CUDA primary, skip ONNX for now)

`src/embed/batch_manager.py` — port from V1 (token-budget batching)

`src/export/packager.py` — write chunks.jsonl + vectors.npy + manifest.json

`src/pipeline.py` — orchestrate: parse → chunk → embed → export

`scripts/run_pipeline.py` — CLI: `python scripts/run_pipeline.py --input test_file.txt`

Test: Run on 1 text file. Verify chunks.jsonl has chunks, vectors.npy has 768-dim float16 vectors, manifest.json has correct metadata.

Exit: CorpusForge produces a valid export package from a single file.

### Slice 0.3: V2 Import + LanceDB + Basic Query (Day 2-3)

`src/store/lance_store.py` — create LanceDB table, insert chunks + vectors, hybrid search

`scripts/import_embedengine.py` — read CorpusForge export → load into LanceDB

`src/llm/client.py` — unified openai SDK client (GPT-4o, GPT-OSS-120B)

`src/query/vector_retriever.py` — LanceDB hybrid search (vector + BM25)

`src/query/context_builder.py` — assemble top-K chunks into context string

`src/query/generator.py` — GPT-4o generation with graduated confidence prompt

`src/api/routes.py` — POST /query endpoint (minimal FastAPI)

`src/api/server.py` — FastAPI app bootstrap

Test: Import CorpusForge export. Ask a question about the test file. Get a sourced answer.

Exit: Question in → answer out, end-to-end through both apps. The skeleton walks.

### Slice 0.4: First Golden Eval (Day 3)

Write 5 golden queries in `tests/golden_eval/golden_queries.json`

`tests/golden_eval/eval_runner.py` — run queries, check fact_score

Verify all 5 produce reasonable answers

This becomes the regression test for everything that follows

Sprint 0 Deliverable: A working system — crude, minimal, but data flows from raw file through both apps to a sourced answer. Every subsequent sprint adds capability to this working skeleton.

## Sprint 1: Core Pipeline (Days 4-8 — April 8-12)

Goal: CorpusForge handles real corpus data. V2 handles real queries with reranking.

### Slice 1.1: CorpusForge — Full Parser Stack (Day 4-5)

Port remaining 31 parsers from V1 into `src/parse/parsers/`

PDF (pdfplumber + OCR fallback)

DOCX, XLSX, PPTX, CSV, MSG, HTML, RTF, JSON, XML, etc.

`src/parse/dispatcher.py` — route files by extension

`src/parse/quality_scorer.py` — port from V1, score 0.0-1.0

`src/parse/ocr.py` — pytesseract + Poppler pipeline

Error isolation: try/except per file, never crash

Test: Run CorpusForge on 100 mixed-format files. Verify parse success rate > 90%.

### Slice 1.2: CorpusForge — Hash + Dedup (Day 5-6)

`src/download/hasher.py` — SHA-256 content hashing

`src/download/deduplicator.py` — _1 suffix + content-hash dedup

SQLite file_state table (path, hash, mtime, status)

Incremental mode: re-run pipeline, verify unchanged files are skipped

Test: Run pipeline twice on same files. Second run processes 0 files.

### Slice 1.3: V2 — FlashRank Reranking (Day 6-7)

`src/query/reranker.py` — FlashRank integration (or LanceDB built-in if waiver pending)

Wire into query pipeline: retrieve top-30 → rerank → top-10

A/B test: run golden eval with and without reranking, measure improvement

Test: Reranking improves fact_score on at least 3 of 5 golden queries.

### Slice 1.4: V2 — Graduated Confidence + Streaming (Day 7-8)

Update generator prompt with graduated confidence (HIGH/PARTIAL/NOT_FOUND)

`src/api/routes.py` — add POST /query/stream (SSE)

Verify streaming works end-to-end

### Slice 1.5: Scale Test (Day 8)

Run CorpusForge on 1,000 real files from production corpus

Import into V2, run golden eval

Measure: LanceDB search latency, total query latency, memory usage

Expand golden eval to 10 queries

Sprint 1 Deliverable: CorpusForge parses 32+ formats, deduplicates, and exports. V2 imports, searches with FlashRank reranking, generates answers with confidence levels and streaming. 10 golden queries passing. Already better than V1.

## Sprint 2: Structured Extraction (Days 9-15 — April 13-19)

Goal: Entity extraction and quality gates. Aggregation and lookup queries work.

### Slice 2.1: CorpusForge — Contextual Enrichment (Day 9-10)

`src/enrich/ollama_client.py` — local Ollama API client for phi4:14B

`src/enrich/enricher.py` — generate context prefix per chunk

Wire into pipeline between chunk and embed stages

Updated export: enriched_text field in chunks.jsonl

Test: Import enriched chunks into V2. Run golden eval. Measure retrieval improvement. Target: 20%+ better fact_score on semantic queries.

### Slice 2.2: CorpusForge — GLiNER2 Entity Extraction (Day 10-11)

`src/extract/ner_extractor.py` — GLiNER2 zero-shot NER on CPU

Entity types: PART_NUMBER, PERSON, SITE, DATE, ORG, FAILURE_MODE

Updated export: entities.jsonl with confidence scores

**Fallback if GLiNER waiver pending:** skip this slice, move to Slice 2.3 with GPT-4o only

Test: Extract entities from 100 chunks. Spot-check 20 for accuracy.

### Slice 2.3: V2 — Quality Gates + Normalization (Day 11-13)

`src/ingest/entity_extractor.py` — GPT-4o second-pass on complex chunks

`src/ingest/quality_gate.py` — confidence threshold (>= 0.7), type-specific validation

`src/ingest/entity_normalizer.py` — controlled vocabulary for sites, part patterns, name cleanup

Site vocabulary YAML (25 IGS sites with aliases)

Part number patterns (ARC-NNNN, IGSI-NNNN, PO-YYYY-NNNN)

`scripts/audit_extraction.py` — quality report (accepted/rejected/reasons)

Test: Import entities from CorpusForge. Run quality gate. Verify: "Pre-Site Survey To Thule AB" normalizes to "Thule". "Annette Parsons, (970) 986-2551" splits correctly. Garbage entities rejected.

### Slice 2.4: V2 — Entity + Relationship Stores (Day 13-14)

`src/store/entity_store.py` — SQLite entities table with indexes

`src/store/relationship_store.py` — SQLite relationship triples

`src/store/table_store.py` — SQLite extracted table rows (Docling, if waiver ready)

### Slice 2.5: V2 — Query Router + Structured Retrieval (Day 14-15)

`src/query/router.py` — GPT-4o query classification (SEMANTIC/ENTITY/AGGREGATE/TABULAR/COMPLEX)

`src/query/entity_retriever.py` — SQLite lookup for entity + aggregation queries

`src/query/table_retriever.py` — Text2SQL via GPT-4o for tabular queries

`src/query/decomposer.py` — sub-query generation for COMPLEX queries

Wire router into main query pipeline

Test: Golden eval expanded to 15 queries including:

"Who is the POC for Thule?" → returns a real name from entity store

"How many maintenance service reports in 2025?" → returns SQL count

"Explain the calibration procedure" → still works via semantic path

Sprint 2 Deliverable: CorpusForge produces enriched chunks + candidate entities. V2 validates, normalizes, and stores entities. Query router classifies questions. Aggregation and lookup queries work for the first time. 15 golden queries passing.

## Sprint 3: GUI + Quality Polish (Days 16-22 — April 20-26)

Goal: Demo-ready GUI with streaming, confidence badges, and all query types. CRAG verification.

### Slice 3.1: V2 — GUI Port (Day 16-18)

`src/gui/app.py` — main Tkinter window (carry V1 aesthetic)

`src/gui/query_panel.py` — query input, streaming response display

`src/gui/source_panel.py` — expandable source citations

`src/gui/theme.py` — dark/light color scheme from V1

Confidence badge (HIGH green / PARTIAL yellow / NOT_FOUND red)

Query path indicator (SEMANTIC / SQL / LOOKUP / MULTI-HOP)

Structured results panel (tables rendered as tables)

Remove: mode toggle, role selector, grounding bias slider

### Slice 3.2: V2 — CRAG Verification Loop (Day 18-19)

GPT-OSS-20B grades response against retrieved sources

If confidence < 0.8: rewrite query, re-retrieve, re-generate

Max 2 retries, then return with [LOW CONFIDENCE] flag

Optional — disable if latency budget is tight

### Slice 3.3: V2 — Advanced Query Features (Day 19-20)

Multi-hop queries via relationship JOIN

Query expansion (synonym matching, acronym resolution)

Parent chunk expansion (retrieve child, return parent for context)

### Slice 3.4: CorpusForge — GUI + Scheduling (Day 20-22)

`src/gui/app.py` — monitoring window (pipeline progress, run history)

`scripts/schedule_nightly.py` — Windows Task Scheduler setup

Headless mode (no GUI, log to file) for nightly runs

`scripts/audit_index.py` — corpus audit report

### Slice 3.5: Golden Eval Expansion (Day 22)

Expand to 20+ golden queries covering all 5 failure classes

Include: aggregation, entity lookup, tabular, synonym mismatch, cross-document

Run full eval, document results

V1 vs V2 comparison on identical queries

Sprint 3 Deliverable: GUI demo-ready with streaming, confidence badges, and all query types. CorpusForge runs on schedule with monitoring. 20 golden queries passing. V1 vs V2 comparison documented.

## Sprint 4: Demo Hardening (Days 23-28 — April 27 - May 2)

Goal: Production-quality on real work data. Demo rehearsed.

### Slice 4.1: Full Corpus Processing (Day 23-25)

Run CorpusForge against full 420K file corpus (background, may take 2-3 days)

Monitor: GPU utilization, memory, disk I/O, timing per stage

Fix any scale issues (file handle limits, SQLite WAL locking, batch OOM)

V2 imports full-scale export, verify all stores populated

### Slice 4.2: Performance Tuning (Day 25-26)

Benchmark all query types on production data

Tune: LanceDB index settings, FlashRank top-N, retrieval depth, RRF weights

Target: P50 < 3s, P95 < 10s

Memory profiling on Beast and laptop

CorpusForge incremental nightly target: < 90 minutes

### Slice 4.3: Demo Prep (Day 26-28)

Prepare 10 demo queries covering all failure classes

Document expected answers for each

Rehearse demo flow: simple → entity → aggregation → tabular → complex

Build "V1 vs V2" comparison (same query, different results)

Final golden eval: 20/20 on production data

Bug fixes, edge cases, polish

### Slice 4.4: Documentation (Day 28)

Update all docs with final architecture

Deployment guide (clean install from scratch)

Operator guide (how to query, read confidence, check CorpusForge status)

Demo script with talking points

Sprint 4 Deliverable: Demo-ready. Production data queried successfully. V1 vs V2 comparison dramatic. Operator docs complete. Ready to show.

## Risk Mitigation

Risk  |  Mitigation

LanceDB waiver delayed  |  FAISS + FTS5 fallback in Slice 0.3

GLiNER waiver delayed  |  GPT-4o handles all extraction (costlier but works)

Docling waiver delayed  |  openpyxl + pdfplumber (lower accuracy but functional)

FlashRank waiver delayed  |  LanceDB built-in reranking (zero deps)

Full corpus enrichment takes too long  |  Kick off Day 9, runs in background. Demo on partial enrichment if needed.

Skeleton doesn't walk by Day 3  |  Stop and debug. Nothing else matters until end-to-end works.

Quality gates reject too many entities  |  Lower threshold temporarily, tune with audit report data

GPT-4o extraction cost exceeds budget  |  Start with high-value docs only (service reports, logistics), expand later

## Milestone Summary

Day  |  Milestone  |  State of System

Day 3  |  Skeleton walks  |  1 file → CorpusForge → V2 → answer. Crude but end-to-end.

Day 8  |  Sprint 1 done  |  32+ parsers, dedup, reranking, streaming. 10 golden queries. Better than V1.

Day 15  |  Sprint 2 done  |  Entity extraction + quality gates. Aggregation works. 15 golden queries.

Day 22  |  Sprint 3 done  |  GUI, CRAG, all query types. 20 golden queries. Demo-able.

Day 28  |  Sprint 4 done  |  Production data, tuned, rehearsed. Demo-ready.

Jeremy Randall | HybridRAG_V2 + CorpusForge | 2026-04-04 MDT